## Regulatory Timeline
MORGAN COUNTY MA CO-OP — REGULATORY TIMELINE PROJECT PLAN
Concept demonstration — generated via the Ledger PM Agent mockup. Not a real regulatory filing.
Phases complete: | 4 | Total phases: | 5 | % Complete: | 80%
Phase | Timeframe | Owner | Deliverable | Status | Risk Flag / Notes
Phase 1: Pre-Application | M1–M6 | CEO | Actuarial solvency memo + service area filing | COMPLETE | None — cleared
Phase 2: CMS Application Submission | M7 | CEO + Compliance Counsel | Full bid submission package | COMPLETE | None — cleared
Phase 3: CMS Review Window | M8–M18 | CMS Regional Office | Approval notice issued | COMPLETE | None — cleared
Phase 4: CDOI Licensure (parallel) | M3–M12 | CEO + Colorado Counsel | Certificate of Authority issued | COMPLETE | None — cleared
Phase 5: Operational Launch | M19 | Full Founding Team | First enrollment period open | BLOCKED | REAL BLOCKER — Vendor network readiness. CMS requires documented first-tier and downstream entity (FDR) agreements before member-facing operations begin. Morgan County vendor pool contracts are unsigned and unvalidated. No launch until FDR agreements are executed and filed.

## Evidence & Assumptions
EVIDENCE LEDGER — CLAIMS BEHIND THIS PLAN
Claim | Type | Confidence | Risk | Source
CMS requires documented FDR agreements before operational launch | factual | 85% | 40% | CMS regulatory pattern
ASSUMPTIONS THIS PLAN RESTS ON
• Phases 1–4 are treated as complete for mockup purposes.
• Vendor network readiness is the sole real-world blocker remaining at Phase 5.
• The Month 19 operational launch target is confirmed acceptable to the founding team.